## Home
LOG BUG
TEXAS GROUP
Created date: 06/05/2015
Severity
Level | Complexity of Bug | Description
1 | Very Basic | Interface Bugs. Bugs can be fixed easily by CSS, HTML
2 | Basic | Data bugs. e.g., Missing files, images, cannot get or found data, etc. Logic bugs. Design bug.
3 | Normal | Bugs affect some functions. Unable to run those functions. State that has these bugs may execute.
4 | Complex | Bugs affect all functions of State. State that has these bugs cannot execute.Bugs are in library.
5 | Very Complex | Bugs affect all functions of Application. Application cannot execute. Bugs have to be fixed immediately.

## 06-05-2015
Last Update: 06/05/2015
ID | Found Date | Bug Description | Severity (1-5) | Files affected | Found By | Fixed By | Fixed Date | Additional Comment
1 | 2015-05-06 | Month Calendar's day labels, Search Filter's avoid and prioritize buttons has wrong color when click on. | 1 | template-month.html, search-filter.html | Ngo Duc Dung | Can Duy Cat | 2015-05-06
2 | 2015-05-06 | Controller 'ionNavBar', required by directive 'ionNavButtons', cant't be found. | 2 |  | Ngo Duc Dung
3 | 2015-05-06 | Unexpected effects when load page | 1 | search-filter.html, my-profile.html. | Ngo Duc Dung
5 | 2015-05-06 | Unexpected effects when click on a card in FriendPanel | 1 | friend-panel.html | Ngo Duc Dung
6 | 2015-05-06 | Design bug: Message button's at Profile page of user. User sends message for themseft ? | 2 |  | Ngo Duc Dung

## 07-05-2015
Last Update: 07/05/2015
ID | Found Date | Bug Description | Severity (1-5) | Files affected | Found By | Fixed By | Fixed Date | Additional Comment
1 | 2015-05-07 | Design bug: Do not reset data when click back function in event form | 2 |  | Can Duy Cat | Nguyen Minh Trang | 2015-05-07
2 | 2015-05-07 | Error when call getCalendar function: this.convertCal is not a function | 3 | search-filter.html, result.html | Ngo Duc Dung | Nguyen Minh Trang | 2015-05-07
3 | 2015-05-07 | Design bug: Do not reset data when click back function in search-filter | 2 |  | Can Duy Cat | Ngo Duc Dung | 2015-05-07

## 09-05-2015
Last Update: 09/05/2015
ID | Found Date | Bug Description | Severity (1-5) | Files affected | Found By | Fixed By | Fixed Date | Additional Comment
1 | 2015-05-09 | When click edit button: "Cannot read property 'summary' of null". When click delete button: "Cannot read property 'events' of undefined". | 3 | edit-event.html, event-detail.html | Ngo Duc Dung